## Sheet1
Week of: | Experiment Goals: | Thesis Goals:
01.08.23 | Launch experiment by the end of January | Draft of Intro
01.22.23
02.05.23 | Debug experiment (should take about 2 weeks) | Draft of Methods
02.19.23
03.05.23 | Experiment Live by early March (2-3 days needed for data collection) | Revise Intro + Methods
03.12.23
03.19.23 | data analysis, conclusions, and implications | Draft Results + Conclusions
04.02.23 |  | Revise Results + Conclusions
04.09.23 |  | Polish Final Paper
04.14.23 | Thesis due at 5pm!